## Sheet1
Meeting 1 / qwerty
Date: | 2025-03-03 | Location:
Time: | 09am | A12
Chaired by | Danyil
Attendees: | Danyil & Artem
Preparation for Meeting
Updated Lab 4 document with annotated use cases
Working demo of database connection
I | Open Meeting
To discuss the current state of the project
discuss soft Eng. and web server CA
II | Action Items from Previous Meeting | Responsible | Due Date
1 | Implement user registration & login form. Post creating functionality | Danyil | 2025-02-23
2 | Functional requirement & non Functional requirement | Artem | 2025-02-23
3 | ERD Diagram | Artem | 2025-02-28
4 | Implement data validation | Danyil | 2025-02-23
5 | Update GitHub repository | Both | 2025-02-23
III | Agenda Topic | Presenter | Duration | Minutes of the meeting
1 | Review Lab 4 deliverables | Danyil | 10 minutes | Demonstrated the database connection and data display functionality
2 | Discuss database implementation | Danyil | 10 minutes | Successfully created database with three tables: Users, Posts, Comments
3 | Plan next development steps | Artem | 10 minutes | Artem will need to implement user authentication system
4 | Assign tasks for next sprint | Artem | 5 minutes | Discuss next sprint tasks
5 | Soft eng testing | Both | 5 minutes | all team members are going to work on the report
6
IV | Close Meeting