## Dining Philosophers Projec - GanttChart.ai
[6 empty] | March 2025 | [6 empty] | April 2025 | [29 empty] | May 2025 | [30 empty] | June 2025 | [29 empty] | July 2025 | [30 empty] | August 2025 | [30 empty] | September 2025
Workstream | Task | Team | Duration | Start Date | End Date | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Research Phase
| Learn about Dining Philosophers problem. | Artem, Daniel & Emanuel | 7 | 2025-03-25 | 2025-04-02
| Study ThreadMentor and Thread concepts. | Artem, Daniel & Emanuel | 7 | 2025-04-03 | 2025-04-11
| Understand programmed solutions. | Artem & Daniel | 10 | 2025-04-14 | 2025-04-25
Setup & Implementation
| Set up ThreadMentor on Linux VM. | Daniel & Artem | 3 | 2025-04-28 | 2025-04-30
| Download solution C++ code. | Daniel & Emanuel | 1 | 2025-05-01 | 2025-05-01
| Create Makefile and compile code. | Daniel & Artem | 2 | 2025-05-02 | 2025-05-05
Analysis & Testing
| Run solution with ThreadMentor. | Daniel, Artem & Emanuel | 5 | 2025-05-06 | 2025-05-12
| Take screenshots of execution. | Emanuel & Daniel | 5 | 2025-05-13 | 2025-05-19
| Analyze synchronization issues. | Artem, Daniel & Emanuel | 7 | 2025-05-20 | 2025-05-28
Mid-Semester Deliverable
| Prepare mid-semester presentation. | Emanuel, Artem & Daniel | 5 | 2025-05-29 | 2025-06-04
| Practice presentation. | All team members | 2 | 2025-06-05 | 2025-06-06